## schedule
Độ ưu tiên | Mô tả | thời gian | công việc
VH | very heigh | 2/2012 | thiết kế hệ thống
H | heigh | 1/3/2012-31/3/2012 | iteration 1
N | mormal | 1/4/2012-30/4/2012 | iteration 2
L | low | 1/5/2012-31/5/2012 | iteration 3
VL | very low | 1/6/2012-25/6/2012 | viết báo cáo, review
|  | 25/6/2012 | Nộp đề tài KLTN
|  | 27/6/2012 – 02/7/2012 | phản biện đề tài KLTN
|  | 17/7/2012 – 18/7/2012 | bảo vệ
|  | 6/8/2012 | nộp khóa luận sau khi bảo vệ
ghi chú
|  | 22/6/2012 – 24/6/2012 | Xin hẹn (qua email) phản biện đề tài KLTN

## Product_backlog
stt | use case | mô tả chung | độ ưu tiên | iteration
1 | create account |  | VH | 1
2 | update account |  | VH | 1
3 | delete account |  | VH | 1
4 | accept account |  | VH | 1
6 | login |  | VH | 1
7 | log out |  | VH | 1
8 | update my account |  | VH | 1
14 | create project |  | VH | 1
15 | update project |  | VH | 1
17 | choose process |  | VH | 1
18 | add member to project |  | VH | 1
19 | remove member from project |  | VH | 1
20 | phan quyen cho cac thanh vien cua project |  | VH | 1
23 | create workitem |  | VH | 1
24 | update workitem |  | VH | 1
26 | view workitem detail |  | VH | 1
5 | search account | duoc dung khi add member vao project | H | 2
9 | update personal calendar |  | VH | 2
10 | view personal calendar |  | VH | 2
11 | create personal calendar |  | VH | 2
25 | delete workitem |  | H | 2
27 | search workitem |  | VH | 2
41 | view project calendar |  | VH | 2
42 | update project calendar |  | VH | 2
44 | view project detail |  | VH | 2
45 | view project's workitems |  | VH | 2
46 | automatically plan a event | tu dong xac dinh thoi gian dien ra su kien dua vao thoi gian ranh cua thanh vien | VH | 2
12 | view workitem assign to me |  | N | 3
13 | view projects activities |  | N | 3
16 | delete project |  | N | 3
21 | ask to join project |  | N | 3
22 | accept member |  | N | 3
28 | link to artifact |  | N | 3
29 | get information about artifact |  | N | 3
30 | get information about changeset |  | N | 3
31 | view project report |  | L | 3
32 | create survey |  | N | 3
33 | update survey |  | N | 3
34 | view survey result |  | N | 3
35 | delete survey |  | N | 3
36 | answer survey |  | N | 3
37 | create wiki page |  | N | 3
38 | update wiki page |  | N | 3
39 | search in wiki |  | N | 3
40 | write on wiki |  | N | 3
43 | remind member about events |  | N | 3