## schedule
Độ ưu tiên | Mô tả | thời gian | công việc
VH | very heigh | 2/2012 | thiết kế hệ thống
H | heigh | 1/3/2012-31/3/2012 | iteration 1
N | mormal | 1/4/2012-30/4/2012 | iteration 2
L | low | 1/5/2012-31/5/2012 | iteration 3
VL | very low | 1/6/2012-25/6/2012 | viết báo cáo, review
|  | 25/6/2012 | Nộp đề tài KLTN
|  | 27/6/2012 – 02/7/2012 | phản biện đề tài KLTN
|  | 17/7/2012 – 18/7/2012 | bảo vệ
|  | 6/8/2012 | nộp khóa luận sau khi bảo vệ
ghi chú
|  | 22/6/2012 – 24/6/2012 | Xin hẹn (qua email) phản biện đề tài KLTN

## Product_backlog
stt | use case | mô tả chung | độ ưu tiên | iteration | Issues
1 | create account |  | VH | 1
2 | update account |  | VH | 1
3 | delete account |  | VH | 1
4 | login |  | VH | 1
5 | log out |  | VH | 1
6 | update my account |  | VH | 1
7 | create project |  | VH | 1 | parent container --> parent project
8 | update project |  | VH | 1 | abort calendar | abort process
9 | choose process |  | VH | 1
10 | add member to project |  | VH | 1 | failed when email not invalid
11 | remove member from project |  | VH | 1
12 | phan quyen cho cac thanh vien cua project |  | VH | 1
13 | create workitem |  | VH | 1 | cannot create workitem when not be member | attachtment | iteration
14 | update workitem |  | VH | 1
15 | view workitem detail |  | VH | 1 | history
16 | search account | duoc dung khi add member vao project | H | 2
17 | update personal calendar |  | VH | 2
18 | view personal calendar |  | VH | 2
19 | create personal calendar |  | VH | 2
20 | search workitem |  | VH | 2
21 | view project calendar |  | VH | 2
22 | update project calendar |  | VH | 2
23 | view project detail |  | VH | 2
24 | view project's workitems |  | VH | 2
25 | automatically plan a event | tu dong xac dinh thoi gian dien ra su kien dua vao thoi gian ranh cua thanh vien | VH | 2
26 | view workitem assign to me |  | N | 3
27 | view projects activities |  | N | 3
28 | remind member about events |  | N | 3
29 | create proccess
30 | edit process |  |  |  | cannot edit
31 | create class
32 | edit class
33 | show class
34 | my project