## schedule
Độ ưu tiên | Mô tả | thời gian | công việc
VH | very heigh | 2/2012 | thiết kế hệ thống
H | heigh | 1/3/2012-31/3/2012 | iteration 1
N | mormal | 1/4/2012-30/4/2012 | iteration 2
L | low | 1/5/2012-31/5/2012 | iteration 3
VL | very low | 1/6/2012-25/6/2012 | viết báo cáo, review
|  | 25/6/2012 | Nộp đề tài KLTN
|  | 27/6/2012 – 02/7/2012 | phản biện đề tài KLTN
|  | 17/7/2012 – 18/7/2012 | bảo vệ
|  | 6/8/2012 | nộp khóa luận sau khi bảo vệ
ghi chú
|  | 22/6/2012 – 24/6/2012 | Xin hẹn (qua email) phản biện đề tài KLTN

## Product_backlog
stt | use case | mô tả chung | độ ưu tiên | iteration
1 | create account |  | VH | 1
2 | update account |  | VH | 1
3 | delete account |  | VH | 1
4 | update my account |  | VH | 1
5 | register project |  | VH | 1
6 | choose process |  | VH | 1
7 | accept project |  | VH | 1
8 | delete project |  | VH | 1
9 | create project |  | VH | 1
10 | update project |  | VH | 1
11 | add member to project |  | VH | 1
12 | remove member from project |  | VH | 1
13 | phan quyen cho các thanh vien của project |  | VH | 1
14 | ask to join to project |  | VH | 1
15 | accept member |  | VH | 1
16 | create work item |  | VH | 1
17 | update work item |  | VH | 1
18 | view work item detail |  | VH | 1
19 | search account |  | H | 2
20 | view work item relate to me |  | N | 2
21 | create personal schedule |  | H | 2
22 | update personal schedule |  | H | 2
23 | view personal schedule |  | H | 2
24 | link to artifact |  | VH | 2
25 | get information about artifact |  | VH | 2
26 | get information about changeset |  | VH | 2
27 | view artifact |  | VH | 2
28 | search work item |  | VH | 2
29 | view project report |  | H | 2
30 | manage project schedule |  | H | 2
31 | view project schedule |  | H | 2
32 | view my activity |  | L | 3
33 | create group |  | N | 3
34 | delete group |  | N | 3
35 | update group |  | N | 3
36 | add member to group |  | N | 3
37 | remove member from group |  | N | 3
38 | update subproject |  | H | 3
39 | create subproject |  | H | 3
40 | delete subproject |  | H | 3
41 | answer survey |  | N | 3
42 | view survey result |  | N | 3
43 | search in wiki |  | N | 3
44 | write on wiki |  | N | 3
45 | view wiki |  | N | 3
46 | manage wiki |  | N | 3
47 | manage survey |  | N | 3
48 | remind member about event |  | N | 3
49 | create area |  | N | 3
50 | update area |  | N | 3
51 | delete area |  | N | 3
52 | view area detail |  | N | 3
53 | add member to area |  | N | 3
54 | remove member from area |  | N | 3
55 | phan quyen thanh vien của area |  | N | 3

## Product_backlog2
STT | Chức năng | Ghi chú
1 | create account
2 | accept account
3 | update account
4 | delete account
5 | search account
6 | log in
7 | update my account
8 | view projects activities | ???what is activities?
9 | view workitems relative to me | các work item có thể thuộc các project khác nhau.
10 | create personal calendar
11 | view personal calendar
12 | update personal calendar
13 | create project
14 | update project
15 | choose process
16 | add member to project
17 | remove member from project
18 | phan quyen cho thanh vien cua project | xác định thành viên làm project management hay là thành viên bình thường
19 | ask to join project
20 | accept member
21 | create work item
22 | update work item
23 | delete work item
24 | link to artifact
25 | get information about artifact
26 | get information about changeset
27 | view workitem detail
28 | view artifact
29 | search workitem
30 | answer the survey
31 | view the survey result
32 | search in wiki
33 | write on wiki
34 | view wiki
35 | create survey
36 | update survey
37 | delete survey
38 | create wiki page
39 | delete wiki page
40 | update wiki page
41 | update project calendar
42 | view project calendar
43 | remind member about events
44 | view project report | chưa rõ cần report gì??