## schedule
Độ ưu tiên | Mô tả | thời gian | công việc
VH | very heigh | 2/2012 | thiết kế hệ thống
H | heigh | 1/3/2012-31/3/2012 | iteration 1
N | mormal | 1/4/2012-30/4/2012 | iteration 2
L | low | 1/5/2012-31/5/2012 | iteration 3
VL | very low | 1/6/2012-25/6/2012 | viết báo cáo, review
|  | 25/6/2012 | Nộp đề tài KLTN
|  | 27/6/2012 – 02/7/2012 | phản biện đề tài KLTN
|  | 17/7/2012 – 18/7/2012 | bảo vệ
|  | 6/8/2012 | nộp khóa luận sau khi bảo vệ
ghi chú
|  | 22/6/2012 – 24/6/2012 | Xin hẹn (qua email) phản biện đề tài KLTN

## Product_backlog
stt | use case | mô tả chung | độ ưu tiên | iteration
1 | create account |  | VH | 1
2 | update account |  | VH | 1
3 | delete account |  | VH | 1
4 | update my account |  | VH | 1
5 | register project |  | VH | 1
6 | choose process |  | VH | 1
7 | accept project |  | VH | 1
8 | delete project |  | VH | 1
9 | create project |  | VH | 1
10 | update project |  | VH | 1
11 | add member to project |  | VH | 1
12 | remove member from project |  | VH | 1
13 | phan quyen cho các thanh vien của project |  | VH | 1
14 | ask to join to project |  | VH | 1
15 | accept member |  | VH | 1
16 | create work item |  | VH | 1
17 | update work item |  | VH | 1
18 | view work item detail |  | VH | 1
19 | search account |  | H | 2
20 | view work item relate to me |  | N | 2
21 | create personal schedule |  | H | 2
22 | update personal schedule |  | H | 2
23 | view personal schedule |  | H | 2
24 | link to artifact |  | VH | 2
25 | get information about artifact |  | VH | 2
26 | get information about changeset |  | VH | 2
27 | view artifact |  | VH | 2
28 | search work item |  | VH | 2
29 | view project report |  | H | 2
30 | manage project schedule |  | H | 2
31 | view project schedule |  | H | 2
32 | view my activity |  | L | 3
33 | create group |  | N | 3
34 | delete group |  | N | 3
35 | update group |  | N | 3
36 | add member to group |  | N | 3
37 | remove member from group |  | N | 3
38 | update subproject |  | H | 3
39 | create subproject |  | H | 3
40 | delete subproject |  | H | 3
41 | answer survey |  | N | 3
42 | view survey result |  | N | 3
43 | search in wiki |  | N | 3
44 | write on wiki |  | N | 3
45 | view wiki |  | N | 3
46 | manage wiki |  | N | 3
47 | manage survey |  | N | 3
48 | remind member about event |  | N | 3
49 | create area |  | N | 3
50 | update area |  | N | 3
51 | delete area |  | N | 3
52 | view area detail |  | N | 3
53 | add member to area |  | N | 3
54 | remove member from area |  | N | 3
55 | phan quyen thanh vien của area |  | N | 3

## Product_backlog2
Chức năng | Ghi chú
create account
accept account
update account
delete account
search account
log in
update my account
view projects activities | ???what is activities?
view workitems relative to me | các work item có thể thuộc các project khác nhau.
create personal calendar
view personal calendar
update personal calendar
create project
update project
choose process
add member to project
remove member from project
phan quyen cho thanh vien cua project | xác định thành viên làm project management hay là thành viên bình thường
ask to join project
accept member
create work item
update work item
delete work item
link to artifact
get information about artifact
get information about changeset
view workitem detail
view artifact
search workitem
answer the survey
view the survey result
search in wiki
write on wiki
view wiki
create survey
update survey
delete survey
create wiki page
delete wiki page
update wiki page
update project calendar
view project calendar
remind member about events
view project report | chưa rõ cần report gì??